## Gantt Chart
PROJECT TITLE
Mecha-Bot
PROJECT START | 2023-03-30
Display Week | 4 |  |  |  |  | 27.03.23 - 02.04.23 | [6 empty] | 03.04.23 - 09.04.23 | [6 empty] | 10.04.23 - 16.04.23 | [6 empty] | 17.04.23 - 23.04.23 | [6 empty] | 24.04.23 - 30.04.23 | [6 empty] | 01.05.23 - 07.05.23 | [6 empty] | 08.05.23 - 14.05.23 | [6 empty] | 15.05.23 - 21.05.23 | [6 empty] | 22.05.23 - 28.05.23 | [6 empty] | 29.05.23 - 04.06.23 | [6 empty] | 05.06.23 - 11.06.23
 | time axis 2023-03-27 to 2023-06-11
TASK | ASSIGNED MEMBER | PROGRESS | WEEK (S) | START | END | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
Problem Definition |  | 100% | 4 | 2023-03-30 | 2023-04-02
Design Specifications |  | 100% | 5 | 2023-04-03 | 2023-04-09
Literiture Survey |  | 60% | 5 | 2023-04-03 | 2023-04-09
Functional Decomposition |  | 0% | 5 | 2023-04-03 | 2023-04-09
Conceptual Design and Evaluation |  | 0% | 6 | 2023-04-10 | 2023-04-16
Detailed Design Assessment and Calculations |  | 0% | 7 | 2023-04-17 | 2023-04-23
Distribution of Tasks |  | 0% | 7 | 2023-04-17 | 2023-04-23
Manufacturing and Test Plan |  | 0% | 8-9-10 | 2023-04-24 | 2023-05-14
Test of Functions and Development of Product |  | 0% | 10-11-12-13-14 | 2023-05-08 | 2023-06-11
Demonstration of Final Product |  | 0% | 14 | 2023-06-05 | 2023-06-11

## Sheet2
This is a dynamic gantt chart - you can change dates by just changing project start date
#NAME?
Link: | https://www.youtube.com/watch?v=un8j6QqpYa0&ab_channel=Vertex42
WRITE : =AND(E$9>=$C11,E$9<=$D11)